# RECOMMENDATION 1

The HEQC recommends that VUT enters into a broad institutional debate about the type of university of technology it wants to become – as a precursor to developing a comprehensive strategy which signals changes in the focus of the three core functions and the nature and scope of its relationship with industry. The strategy should indicate a timeframe and the level of resource allocation necessary to support the institution’s transition from a technikon to a university of technology.

KEY PRIORITIES

Institutional Operational Plan (IOP) : timeframes and resource implications Align resource allocations with strategic priorities Strategy and timeframe to implement HEQF influence on curriculum/ PQM/ WIL (student profile, programmes, type of research Set expectations and benchmarks for departments and staff

OBJECTIVES Conceptualisation of the type of institution Integration of plan and resources to support the transition process Continuous benchmarking of trends and good practice at UoT’s internationally preferred status Establish strategic networks to optimize capacity, excellence and recognition locally and internationally

STRATEGY Establish VUT as a leading UoT internationally

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Integrate plans and resources | Develop plans: Institutional Operational Plan Enrolment Plan Resources Plan Developed strategic initiatives and financial forecast for period 2009 – 2014 Operational plans informed by plans on strategic and tactical levels Resources are allocated in order to support implementation of VUT strategic objectives | Plans aligned with strategic initiatives Integration of plans and resources Operational plans link with strategic and tactical plans Adequate resources to support implementation of plans | Rectorate | Five year budget growth of approximately R 500m Infrastructure Development Investment approximately R250 m (2009- 2013) Investment in addressing staff/FTE ratio at approximately R 20 m p.a | 2009 - 2014 | Establish mechanisms to ensure that plans on strategic and tactical levels cascade into operational plans Redirect actual enrolment towards DoHET agreed enrolment targets to ensure no non-funded students (DoHET) Adjust budget towards critical academic support needs to address graduate benchmarks |
| Establish strategic networks | Align with national and international networks to ensure relevance through participation Establish new relationships Assess existing collaboration agreements Preferred types of collaboration | Productive partnerships with preferred collaboration institutions VUT preferred institution i.t.o. of postgraduate, postdoctoral students and exchange academics i.t.o. academic focus areas | DVC: Academic and Research | Annual budget to facilitate specific collaboration activities | 2007 – Ongoing | Conduct detailed analysis of existing agreements and relationships Clean up the relationships to retain the productive agreements Determine criteria for new relationships |
| Continuous benchmarking of good practices at UoT’s | Align South African Technology Network (SATN) national Performance Indicators (PI’s) with institutional plans and activities Monitoring and implementation Quality Improvement Teams established and workshops arranged for integration of PI’s with quality assurance minimum standards | Performance indicators (PI’s) for VUT meet UoT characteristics | DVC: Academic and Research Director Quality Promotion | QPU annual budget | 2010 – Ongoing | SATN PI’s and HEQC/VUT minimum standards should be utilised during reviews Develop a system for the dissemination of management information between Information Technology Services (ITS)/ Institutional Planning Unit (IPN) and Quality Promotion Unit (QPU) Integrate PI’s to the quality assurance system and pilot test during reviews |
|  | Develop New Generation Universities (NGU) characteristics and integrate into VUT strategy Introduce NGU characteristics into academic plan and institutional activities | PI’s integrated into operational plans | DVC: Academic and Research | Specific allocation for academic planning | 2007 – Ongoing | Characteristics integrated into the Academic Plan Continue the institutionalization process Integrate PIs into business unit plans |

# RECOMMENDATION 2

The HEQC recommends that the VUT uses its own broad definition of transformation to introduce issues of academic quality and excellence in order to move from a view of transformation as change in the student demographic profile to one that includes equity of opportunity and success. This should include the introduction of approaches to teaching and learning that take diversity into account, especially with regard to the English-language proficiency of students and staff.

KEY PRIORITIES

Support for teaching and learning approaches Language proficiency support Preparation for learning and academic support Modes of teaching and assessment Integrated learning support from student counseling

OBJECTIVES Present products and services relevant to the development and transformation needs of SA as visible in the national agenda for the development of the country Develop curricula appropriate to support the capacity and citizen requirements of the country Create entrance opportunities and support processes that will optimise the openness of learning opportunities as well as the retention of students Create a learning environment appropriate to the learning needs

STRATEGY Implement a continuous Transformation Agenda to optimise relevance and accessibility of academic activities

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Revisit products and services within the context of the national agenda in relation to local reality and needs | Continuous process Informs planning on operational levels Annual assessment of progress and definition of focus for next year | Products and services that demonstrably contribute to addressing the human resource and knowledge requirements of SA | DVC Academic Exec Deans | Dedicated allocation to fund Cur Dev. | Ongoing | Develop new Programme Qualification Mix (PQM) Approved by Senate Revisit curricula in relation to new PQM |
| Continuous assessment of the scenario within which the VUT execute its mandate | Environment Scans and plans – See Academic Planning Document | Definition of key aspects relevant to the definition of the VUT mandate | DVC Acad Exec Deans | Dedicated allocation to fund Curriculum Development | Ongoing | Exercise completed as part of academic planning purpose Two yearly reviews |
| Continuous process to enhance equity profiles through access initiatives and retention for success programmes | Continuous revision of access initiatives (policy revision), programme evaluations and external peer reviews inform enhancement of programmes and retention of success programmes. MI (Management Information) informs processes to align equity Early warning system to identify “at risk” students | Senate approved entrance requirements Requirements for FET students approved by senate Equity profile of students Well defined and functional entrance processes | DVC Acad Exec Deans HOD’s Manager Unit for Preparation Programmes (MUPP) | Dedicated allocation to fund Curriculum Development | Ongoing | Establish a preparation and introduction programme to enhance access Establish an early warning system to monitor success and retention Continuous peer and other reviews to determine relevance of services |
|  | Revised foundation programmes facilitate wider access Design, develop and implement prep programmes for all faculties Introduce foundation programmes to all faculties Introduce tutor system English proficiency and literacy: English Development Laboratories(EDL) labs increased (4 at main campus, 3 at EduCity, 1 each at Ekuhurleni and Secunda - 9 in total) Extended laboratory national time from 6 months to 1 year (compulsory all students) International student support – basic English – academic and survival skills (EDL lab) Academic staff research on English proficiency literacy and programme for improving of English in academic environment. | Pre-diploma programmes to attract and retain students Retention and success ratios Office established Extra tutors employed 3 weekly periods in time table all students Labs open 8:00- 18:00 & 8:00 – 14:00 Saturdays Positive feedback from Faculties and students Improved student performance | Manager UPP (MUPP) MUPP MUPP MUPP Me E Heuer Deans Head Communication Dept (HCD) HCD HCD HOD’s Director Curriculum Development Facilitator Tutor System | UPP budget More admin support Fixed term contract staff to be used Dedicated allocation of funds | 2009 Ongoing 2010 ongoing 2010 - 2011 | Continuous monitoring of student progress throughout these programmes Annual revision of all pre-diploma programmes More admin support required Introduced system : EduCity Arrangements to be in place in 2011 when Educity campus return to main campus – main campus facilities insufficient to accommodate these students It support withdrawn in 2010 Need to provide additional technical support for EDL |
| Revisit the curricula of all qualifications to determine the relevance thereof | This forms part of the Phase 1 of the 3 Phase implementation plan of the new PQM Short Learning programmes to be designed for administrative staff Aptitude interests tests – to inform teaching and learning strategies, academic support initiatives National Benchmarking Test (NBT) to profile skills of all new students for the design of learning environment and consideration in Curriculum Development Training of tutors, monitoring – student feedback informs enhancement of tutor system Quality assurance activities for tutoring planned for 2010-2011 Develop a Curriculum Development process to standardize initiatives towards optimal quality Establish Cur Dev Committee to monitor process and new curricula Introduce Curriculum Teams to develop new curricula | Revisit all curriculum in terns of HEQF and PQM Focus on developing curricula to meet mandate as UoT Develop integrated curricula to make provision for skills and competencies as well as learning requirements of students Number of new curricula completed In 2010 will change 50% of existing programmes to comply with the HEQF | Director Curriculum Development | Dedicated allocation to fund Curriculum Development | 2010 | Need to capacitate the Curriculum Development function |
| Introduce continuous cycle of revisiting/ re- development of curricula | First audit of all introduction and foundation programmes to be performed Introduce peer evaluation systematically across the institution including practical work | Implementation of the re-visiting/ re-development of curricula | Director Quality Promotion Dir Cur Dev MUPP |  | 2010 - 2011 | Plan revision cycle Develop standards Integrate South African Technology Network (SATN) PI’s Pilot revision and feedback |

# RECOMMENDATION 3

The HEQC recommends that VUT develops a systematic process for SRC officials to be inducted and trained in the principles and structures that inform academic governance so that student representatives can become important agents of change at the institution, as well as active drivers in achieving institutional-level goals which particularly affect their constituency.

KEY PRIORITIES

Development of the SRC Constitution Implementation of training and development programmes for newly elected SRC Recognition of SRC as important role players within the VUT Development of policies and procedures e.g. Code of Conduct for residence students

OBJECTIVES To achieve uniformity in student governance across VUT campuses To align student governance to broader VUT vision and mission and strategic plan To empower SRC so that they can be effective

STRATEGY Benchmarking with other higher education institutions Consultation with all internal and external stakeholders

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Development of the SRC Constitution | Benchmarking initiatives – identify best practice on national level | SRC Constitution compares with good practice with regard to content SRC constitution is approved and implemented | Executive Direct or Student Support Services and Director Student Life and Governance | Approved budget | 2009 Ongoing | Revision of policy in 2011 |
| Training and Development programmes | Inauguration and induction training – programme Election of students on Quality Improvement Teams(QIT) Training of QIT members | Informed stakeholders Positive feedback on training Positive report - training outcomes | Direct or Student Support Services and Director Student Life and Governance Director QPU | Approved budget | Annual | Outcome of reviews will feed into refinement of training programmes Elected and trained members on QIT’s |
| Recognition of SRC as important stakeholder | Participation of SRC in various committees e.g. concession committee, student management liaison committee, tender process committee, quality improvement committee | Attendance of meetings Impact on operational issues | Direct or Student Support Services and Director Student Life and Governance | Approved budget | Ongoing | SRC member to be elected on Quality Promotion Committee |

# RECOMMENDATION 4

The HEQC recommends that VUT looks at partnerships with industry as a necessary condition for the institution to claim a strategic role in relation to technology and the world of work. This focus could include strengthening existing partnerships and the development of new ones, as these is a necessary condition for the successful implementation of work-integrated learning and responsiveness to the world of work, both of which constitute fundamental elements of a UoT.

KEY PRIORITIES

Involvement of industry in curriculum design to ensure market responsiveness Interaction and collaboration with Industry Increase third stream income Development of EducCity area Develop strategic relationships with business leaders and with the Local Municipalities Implementation and follow-up of marketing and media strategies

OBJECTIVES Develop a PQM relevant to VUT as a UoT within the context of the institution Develop key academic focus areas for the VUT Ensure the responsiveness of the VUT to the Human Resources and knowledge development needs of South Africa in the African and global context.

STRATEGY Develop a relevant, dynamic and responsive PQM Establish and Innovation Culture based on continuous stimulation of creative knowledge, information and Intellectual Property (IP) Development

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Conduct a market and trend analysis i.t.o. knowledge and skills requirements in the immediate, national and wider knowledge environment | Environment scan and academic planning exercise informs planning on operational level | Defined market needs and trends relating to knowledge and skills requirements | DVC Academic and Research Executive Deans Academic Planning Forum | Dedicated annual Academic Planning budget Cur Dev Reps Cur Dev budget | 2007 Ongoing | Scanning exercise to be completed in 2009 to inform PQM Alumni and graduate surveys conducted Faculty Management Sciences Appointment of Cur Dev Reps Training of Cur Dev Reps |
| Develop a definition of the nature and characteristics of the type of knowledge and skills required towards the next 10 to 15 yrs | Industry involvement in curriculum design to ensure market responsiveness Advisory board meetings and inputs inform curriculum development processes Contract research : Cooperation with 13 national bodies Memoranda of understanding (MoU) (research related) 19 MOU’s signed with bodies on national and international levels (see Progress Report) Technology Transfer and Innovation : Design Working with and for industry, individual entrepreneurs and innovators. | Life-long learning opportunities Definition of graduateness of VUT High industry involvement in curriculum design to ensure market responsiveness Alignment with UoT’s and Technology stations as well as Industry and science councils e.g. Aerosud, CSIR, SABS | DVC Acad Exec Deans HOD’s Research Directorate Technology Transfer Directorate | Dedicated annual Academic Planning budget Cur Dev Reps | Ongoing | Exercise completed as part of Academic Planning process Appointment of Cur Dev Reps Training of Cur Dev Reps Roll out of plan as part of Acad Plan |
| Formulate the characteristics of the type of competency profile expected from graduates by industry and the broader society | Academic Planning Exercises ; See Academic Planning Working Document Industry involvement in curriculum design – advisory board meetings Curriculum Development workshops Develop the priority focus areas for reseach and academic programmes | Appropriate entrance and exit opportunities to facilitate individual needs Provision for extended programmes to accommodate students not sufficiently prepared for HE learning | Exec Deans HOD’s Dir Cur Dev Cur Dev Reps | Dedicated annual Academic Planning budget Cur Dev budget | Ongoing | Exercise completed as part of Academic Planning process Industry surveys conducted at Management Sciences Appointment of Cur Dev Reps Training of Cur Dev Reps Roll out of plan as part of Acad Plan |
| Determine the key academic focus areas of the VUT | Working according to the 3 phase implemtation plan for the HEQF Submission of programmes to DoHET, CHE and SAQA | Defined market needs and trends relating to knowledge and skills requirements Completed PQM meeting HEQF criteria Approved PQM by Senate and DoE | DVC Academic Executive Deans Dir Cur Dev Cur Dev Reps | Dedicated annual Academic Planning budget Cur Dev budget | 2010 Ongoing | Key Academic Focus Areas – identified as part of Academic Planning process Appointment of Cur Dev Reps Training of Cur Dev Reps |
| Develop a programme and qualifications framework appropriate for the VUT to meet its mandate as a UoT in its context within the parameters of the new HEQF | See Academic Working Plan Implementation of 3 phase plan for HEQF Advisory boards inputs Curriculum Development teams to be activated. Qualification Committee participate in SATN programme Degree designators to be developed for new qualifications Development of generic first semester / year programmes per discipline environment. | Relevance to the SA global context in information society Effective articulation options to enhance mobility and flexibility Completed PQM meeting HEQF criteria Viable and appropriate qualifications Approved PQM by DoE Generic first semester/ year programmes to facilitate the preparedness/ foundation of students for learning | Dir Cur Dev | Curriculum Development budget Cur Dev Reps | 2010 Ongoing | Developed PQM Approved by Senate Appointment of Cur Dev Reps Training of Cur Dev Reps |
| Develop a clear definition and criteria for innovation and entrepreneurship development at the VUT | Process to continuously stimulate knowledge creation and harvest potential commercialization options Integration into curricula Development of entrepreneurship module for implementation across all faculties | Innovation approach at VUT defined | Executive Director Technology Transfer Information (TTI) Dir Cur Dev | Dedicated Cur Dev budget | Ongoing | Process to refine the definition and criteria for innovation and entrepreneurship Process to develop entrepreneurship component into all curricula |
| Institutionalisation drive to ensure the internalization of the innovation and entrepreneurship approach | Planned initiatives in order to ensure the development of internalization of innovation and entrepreneurship at the VUT | Awareness programmes Training initiatives | Exec Dir TTI Dir Cur Dev | Dedicated Cur Dev budget | Ongoing | Process to develop entrepreneurship component into all curricula |
| Establish an institutional process to continuously identify innovation opportunities and support the development thereof | Development of processes and procedures Information sessions Implementation plans Institutional benchmarking | Number of innovations delivered Clear process on how innovation is approached and supported to guide staff towards innovation action | Exec Dir TTI Exec Deans HoD’s | Dedicated Cur Dev budget | Ongoing | Established interaction between research, teaching and learning and Innovation Office to harvest new ideas for potential innovation on continuous basis |
| Integrate entrepreneurship and innovation into all curricula to ensure all graduates have this capacity and orientation | Participate actively in curriculum teams To integrate entrepreneurship and innovation | Programme context | Exec Dir TTI Dir Cur Dev HoD’s | Dedicated Cur Dev budget | Ongoing | Process to develop entrepreneurship component into all curricula Appointment of Cur Dev Reps Training of Cur Dev Reps |
| Establish networks and funding support options to strengthen the growth of innovation and entrepreneurship | Establish networks Maintain networks Assess impact | Profile and activities of networks in relation to innovation and related entrepreneurship initiatives | Exec Dir TTI | Dedicated budget | Ongoing | Continuous process of recruiting donor funding Cotninous process to establish networks to enhance innovation capacity |

# RECOMMENDATION 5

The HEQC recommends that VUT develops a planning framework that includes the capacity to translate goals into sustainable strategies, the documentation and communication of decisions, and a systematic collection of information for decision-making and monitoring – supported by an integrated and working MIS which includes resource allocation for the main campus and satellites. Such a planning framework should also identify performance indicators, as well as RESPONSIBILITY for implementation, and reporting lines.

KEY PRIORITIES Strategy Plan Review Establishment of dedicated Management Information System Unit Infrastructure Planning Link Planning and Quality Initiatives

OBJECTIVES Develop an Integrated Planning Framework for VUT Translate Strategic Plan within Framework

STRATEGY Engage Units on business remodelling Develop benchmarks within scope and affordability Introduce incentives linked to performance of empoyees

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Establishing/ revision/ restructuring/ alignment of operational functions | Established a Planning Unit (MIS within the Unit) Roll out function of IPU Quality Assurance Operational Framework links and supports functions of Planning Unit | Reliable Data Reliable Reports Customer satisfaction Effective and informed decisions Framework based on benchmarking and research VUT functions integrated: quality management, planning and resource allocation (based on systems theory) On par with HEQC and national/ international benchmarks for quality management and planning at Institutions of Higher Learning | DVC Resources and Planning Director Quality Promotion | As per IOP Quality Promotion Unit Quality Promotion Structures IPU | N/A Ongoing | Integration of Quality Assurance information into planning Functions underpin by the systems theory Research Framework for the integration of quality management, planning and resource allocation based on continuous improvement System that gathers and disseminates reliable quantitative and qualitative information |
| Integration of tactical plans | Enrolment Planning aligned to Infrastructure Plan | Resources determines enrolment Revision of plans on continuous basis | Rectorate | NA | Dec 2012 | Review plans in terms of affordability |
| Integration of Strategic Plan and tactical/operational plans | Development of an Institutional Operating Plan (IOP) | All decisions informed/ based on IOP All plans on tactical and operational level link with Institutional Strategic Plan All quality reviews reflect on implementation of plans | DVC Resources and Planning Director QPU | N/A Quality Promotion PI’s and Standards QPU structures | N/A 2010 | Review progress on implementation of plans Adjustments based on quality reviews and Management Information Align minimum standards and PI’s with plans |

# RECOMMENDATION 6

The HEQC recommends that VUT reviews its conceptualisation and implementation of quality assurance, including the location of the quality assurance function within management structures and its resourcing. This review should take stock of all the steps of evaluation, including quality improvement and monitoring and their potential role in supporting the achievement of institutional-level objectives at departmental and faculty levels. The result of this review should be that quality objectives, measures, implementation timeliness and management accountabilities are clearly understood at the different levels of the institution.

KEY PRIORITIES

Quality policy and system with emphasis on integration of planning and quality Structural changes : Context of a centralised-decentralised system New standards New evaluation methods Initiatives to integrate quality and planning in order to make informed decisions Continuous improvement

OBJECTIVES Establish a quality culture integrated to the total business of the VUT Ensure appropriate understanding and capacity to implement a quality approach in all academic activities of the VUT

STRATEGY Create quality culture through appropriate institutional arrangements and continuous quality assurance and development

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Re-visit the philosophy and strategy to drive a quality approach at VUT based on the HEQC criteria and SATN performance indicators | Drafting of Conceptual Document Develop criteria on par with HEQC requirements and SATN performance Indicators | Academic quality assurance approach, mechanisms and procedure developed and implemented | Dir Quality | QPU Budget QPU staff (Director, Quality Manager and Junior Administrator) | 2009 – 2010 | Development/ revision of Quality Policy Approval of Policy Development of Quality Manual |
| Develop a structure to engage all functions in the implementation of the quality approach | Establish Quality Improvement Teams Establish Quality Promotion Committee (sub-committee of Senate) | Operational structure to drive the quality process in the academic portfolio and in relation to support services | DVC: Acad Dir Quality | QPU Budget QPU staff (Director, Quality Manager and Junior Administrator) | 2009 – 2010 | Develop model and structure In process to operationalise structures Training of Teams |
| Establish and implement a continuous process to monitor quality and facilitate improvement where necessary | Development of Conceptual Document Process for continuous improvement based on PDCA (Plan, Do, Check, Act) model | Continuous process of quality assurance and improvement | Director QPU Manager QPU | QPU Budget QPU staff (Director, Quality Manager and Junior Administrator) | 2009 | Pilot test PIRI (Planning Implementation Review and Improvement) model Completed cycles of evaluation all four faculties and programmes at sites of delivery |
| Present work sessions and training programmes together with the monitoring activities to develop staff, understanding, capacity and commitment | Planned workshops on quality assurance system Pilot testing of implementation of mechanisms/ system Satisfaction surveys Peer review of quality assurance system | Relevant staff attended work sessions and implements mechanisms/ QPU Policy Informed QIT’s and staff | Director QPU | Budget: see above Printing of questionnaires – CSX Company Transport, honoraria, accommodation, etc of external panel members | 2010- Ongoing | Training of all members Development of questionnaires Refine system Information should feed into planning |

# RECOMMENDATION 7

The HEQC recommends that VUT develops a system of benchmarking with relevant local and international universities of technology, one which could help the institution to measure its progress in becoming a university of technology. Part of this system of benchmarking should include the systematic assessment of employer and client satisfaction.

KEY PRIORITIES

Feedback reports from institutional visits and conferences should obtain a section on benchmarking Advisory committees Assessment of employer and customer satisfaction International benchmarking

OBJECTIVES Develop and implement initiatives that ensure continuous feedback on national and international levels with regard to institutional good practices Develop and implement mechanisms in order to conduct satisfaction surveys

STRATEGY Encourage benchmarking activities on local, national and international levels in order to measure the VUT’s enhancement towards becoming a leading UoT.

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Benchmarking Develop mechanisms for continuous feedback | Design questionnaire in cooperation with other UoT’s in order to compare outcomes of satisfaction surveys Design satisfaction survey questionnaires for employers and alumni Participation on national level e.g. SATN Performance Indicators project that inform programme and department quality assurance criteria | Aligns with national and international standards (best practice) | Director Quality Promotion HOD’s Director Research |  | 2010 and ongoing | All feedback reports from institutional visits/conferences to obtain a specific section on benchmarking Survey outcomes informs planning/ adjustments and decision making |
|  | Conduct surveys with staff, students (internal stakeholders) and link with programme and departmental evaluations Feeds information into planning (quality reports) | Statistical data available for interpretation and planning purposes | Director Quality Promotion HOD’s QIT’s |  | 2010 Ongoing | Refine questionnaires |
|  | QPU reports inform planning processes Meetings with advisory boards Outcomes of external peer reviews – recommendations by peers feed into planning and remedial action processes | Feedback on best practices informs enhancement of core business Evaluation reports available on intranet for identification of best practices and for internal benchmarking purposes | Director Quality Promotion HOD’s QIT’s |  | Ongoing | Regular meetings with advisory boards and impact of boards on curricula Accessibility of reports on intranet |
|  | Integration of relevant PI’s into plan with relevant criteria for measurement | Clearly defined PI’s for UoT’s are utilised | Director Quality Promotion |  | 2010 | Relevant PI’s to be identified |

# RECOMMENDATION 8

The HEQC recommends that VUT takes steps to restore external stakeholder and partner confidence which has been partially affected by the impact of the institutional crisis in the abilities of its graduates, but further this lack of confidence also seems to be related to the actual quality of VUT graduates. All of this seem to be more focus on marketing than on substance, which is the point of the recommendation. What substantive actions in relation to the core functions will VUT take to restore confidence?

KEY PRIORITIES

Restoration of confidence with regard to the quality of graduates Aggressive marketing of the new dispensation with regard to instructional management

OBJECTIVES Target main partners with regard to Marketing Structured actions and plans with regard to Marketing

STRATEGY Establish plans to inform partners/external stakeholders Expose partners/ stakeholders to the new campus environment, management developments and institutional well being

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Develop strategy to market the institution | Identification of projects and stakeholders | Donor register is updated and available | Executive Director Corporate Affairs | Unit budget and Rectorate contributions | 2010 Ongoing | Approval and implementation of VUT Foundation to become operational |
|  | Development of initiatives to inform and expose stakeholders to the new campus environment, developments, management and institutional focus areas | Plans are in place Resources are allocated Informed stakeholders Positive attitude of stakeholders Stakeholder investments increased Stakeholder satisfaction | Exec. Director Corporate Affairs | Unit budget | 2010 Ongoing | Implement plans and strategy |
|  | Develop marketing tools and mechanisms that will enhance aggressive marketing strategy | High quality CD Corporate image is positive | Exec. Director Corporate Affairs | Dedicated allocations | 2010 Ongoing | Resources to be allocated (HR and finances) |

# RECOMMENDATION 9

The HEQC recommends that VUT develops a plan to ensure that students and staff at satellite campuses are supported at an acceptable level of quality, while simultaneously considering the future of these campuses

KEY PRIORITIES

Marketing of satellites Strategic plan : outlines future and sustainability of all sites of delivery Industry involvement : Ekurhuleni and Secunda region Collaboration with other HE providers in different regions NIHE collaboration Provision of learner and academic support on all sites of delivery

OBJECTIVES Develop a plan that ensures the enhancement of quality of the core business at satellite campuses Develop a plan with regard to the future of individual sites of delivery

STRATEGY Implement plans in order to ensure continuous improvement and quality of teaching and learning that aligns with the academic standards of the Vanderbijlpark campus

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Phasing out plan - Klerksdorp campus | See Phase-out plan | See Phase-out plan | DVC Academic | Not applicable | 2008- 2009 | Process completed |
| Develop mechanisms that will ensure ongoing improvement of the core business at sites of delivery | Strategic Plan per campus Initiatives on operational level to align satellite campuses with main campus Introduction of extended support services to improve the quality of learning Improve facilities See Progress report Joint departmental meetings HoD’s involved with appointment of staff at sites of delivery | Effective communication between main campus and sites of delivery | DVC Academic HoD’s Head of Academics Academic staff | Part of normal operational budget per year | 2008 -Ongoing | Finalise Strategic plans for Secunda and Ekuhurleni completed Upington in process of reallocation of functions – to National Institute of Higher Education (NIHE) |
|  | Develop quality assurance system for sites of delivery – aligned with main campus Develop suitable criteria Conduct programme evaluations – linked to programmes under evaluation at main campus (quantitative and qualitative mechanisms) Develop policy, guidelines, procedures., etc. Training – workshops on implementation of policy and procedures Report writing following by remedial actions and re-planning/ resource allocation. | Quality assurance system that is effective and on par with main campus system | Director QPU Campus Directors Head Academics HoD’s | QPU budget Director QPU and Manager QPU | Ongoing | System to be developed/ refined Establishment of QIT’s for satellites Training of QIT’s at satellites |
| Develop and implement English Proficiency Programmes for sites of delivery | 4 EDL labs on main campus, 1 per site of delivery and 3 at Educity established (see Progress Report) | Senate and Council support initiatives | Campus Directors Head Dept Education | Dedicated budget | 2009- 2010 |  |
|  | Staff at Ekuhurleni trained on programme design (see Progress Report) | Staff Development | Dir Cur Dev |  | Ongoing |  |

# RECOMMENDATION 10

The HEQC recommends that VUT reconsiders the total student experience at the main and satellite campuses, giving special consideration to the most effective and efficient support it can provide in furthering the health and well-being of its students.

KEY PRIORITIES

Instill a sense of belonging, pride and ownership Decentralisation of services Training and development of coordinators

OBJECTIVES Target student organisations Structural image building programmes to support student life for VUT Ensure that all students have equitable access to services Build capacity of staff to ensure effective support

STRATEGY Establish a working relationship between Corporate Affairs and Student Support Services to promote healthy student life through developmental programmes for student population Make use of Alumni related activities/ initiatives to paint a positive picture regarding the role of Alumni Develop capacity building programmes for staff Sourcing of services from external providers e.g. Accommodation Monitoring and evaluation of services

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Develop a strategy to market the university and its programmes to all VUT students | Identification of projects to match needs of different target groups of students | Make available a list of earmarked annual developmental project plans for students | Corporate Affairs and Student Support Services | Make provision for such projects under institutional marketing budget | 2010 Ongoing | Cooperation and coordination between Corporate Affairs and Student Support Services |
| Develop a strategy to create a sense of belonging and ownership | Develop initiatives through the Alumni office to educate and create awareness regarding the role of Alumni | Develop annual programmes/ initiatives for all students | Alumni Officer | Sponsorships Alumni role models Departmental budget | Annually Ongoing | Fully functional Alumni Office |
| Decentralisation of services | Develop capacity building programmes for staff | Capacitated staff | Director: Student Residence | Student Support Services (SSS) and Campus budget | Ongoing | Align with skills development plans |
| Sourcing of services from external providers e.g. accommodation | Site visit to access accommodation needs | Develop a report from the site visit | Director Student Residence | Dedicated budget from top management | 2010 | Transportation Align accommodations to the university infrastructural development plans. |

# RECOMMENDATION 11

The HEQC recommends that VUT gives urgent attention to the development and implementation of an effective management information system, a system which will serve as a platform for informing and integrating planning, resource allocation and quality improvement in core functions.

KEY PRIORITIES Development of an effective Management Information System Data Access and Security policy Communicate use of data procedure to relevant persons

OBJECTIVES Establish an efficient MIS Guide planning and quality improvements

STRATEGY MIS section to be located in the Planning Unit Provide user friendly reports from a single source

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Establish sound system for the generation and dissemination of Management Information | ( Development of Standard MIS reports from Institutional Planning Unit (IPU) ( Revision of Data Access and Security policy | Satisfied users Suitable reports for decision-making No queries from External Auditors | Executive Director IPU Mr Y Naidu | Currently in place | Ongoing | Workshops with staff Concensus with regard to reporting criteria |
|  |  | Information reliable (quantitative and qualitative) and suitable for planning and decision making | Director QPU | Currently in place | 2010 | Integration of information of quality management tendency/ reviews Reports feed into planning on all levels |
| Revision of relevant policies | Revision of Data Access Policy Revision of Security Policy | No queries from External Auditors Implementation of policies Policies are aligned with best practice | Executive Director IPU Executive Director ITS | Currently in place Currently in place | Dec 2010 Dec 2011 | Appointment and approval levels – alignment to external auditors reports Policy revision schedule, conduct and approval |

# RECOMMENDATION 12

The HEQC recommends that VUT puts necessary mechanisms and resources in place to strengthen the management of WIL. This should include paying particular attention to the place of WIL in curriculum design, and to ensuring that the placement of students is efficiently accomplished and adequately monitored – in order to achieve the relevant teaching and learning objectives of this activity in the different programmes.

KEY PRIORITIES

Implementation of alternative strategies Enhance monitoring of WIL students Appoint WIL sub-committee as part of the HEQF implementation strategy

OBJECTIVES Establish appropriate capacity to extend WIL support to all programmes Train staff and students to participate in WIL process Continuous extension of a network of placement opportunities Establish network of industry experts to assist in assessing the WIL programme

STRATEGY Integrate WIL into all curricula Develop diverse options to facilitate WIL over and above placement in industry

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Aligning of the majority of programmes with WIL component on par with national requirements | New programme development process to be informed by the HEQF prescriptions Workshops – Programme developers (WIL components to be included on par with requirements) Implementation of alternative strategies: parallel stream to integrate WIL into all programmes as alternative to WIL placement in industry (WIL to become a programme) | Programmes with WIL components - aligned with national requirements (e.g. HEQC Accreditation Document and HEQF prescriptions) | Dir Cur Dev HoD’s Cur Dev Reps | Cur Dev Reps | 2009 - ongoing | Appointment of Cur Dev reps Training of Cur Dev Reps |
| Enhance monitoring of WIL students | See Progress Report Proposal to Academic Board for implementation in 2010 (pilot) Best practice/ benchmarking : Engineering Faculty Align/ revise quality assurance mechanisms to focus on monitoring of WIL – programme evaluations | Effective monitoring and support of all WIL students – on par with regulations and requirements | Dir Cur Dev Dir Coop Educ Dir Quality Promotion | WIL funding Cur Dev Reps Cur Dev budget | 2010 Ongoing | Communicate with Deans about work packages and workload of WIL lecturers Appointment of Cur Dev Reps Training of Cur Dev Reps |
| Establish alternative WIL opportunities | Develop alternative methods in collaboration with professional bodies and industry Departments Applied and Computer Science – pilot run Outcomes inform and enhance process Best practice identified and internal benchmarking | On par with national/ professional bodies requirements Pilot testing of concept to enhance process Internal benchmarking Approved by Academic Board and Senate | Exec Deans HoD’s Dir Coop | Development funding | 2010- ongoing | Liaise with industry or private/ established simulation providers (Pilot Electronic Comm) |

# RECOMMENDATION 13

The HEQC recommends that VUT gives attention to the development of a comprehensive IT plan in order to facilitate the development of a platform for strategic planning and decision-making in its core functions. The plan should include: the configuration of IT support; assignment of responsibilities for information management; the adequate resourcing of IT; and the communication of IT functions, role and responsibilities within the institution.

KEY PRIORITIES

Hybrid library and appropriate use of learning management systems (LMS) Business process automation through ICT solutions Compliance with auditor’s recommendations Connected collaborative campus Ensure business continuity on ICT services

OBJECTIVES Revise Appropriate use of ICT facilities policy Automate data maintenance of the LMS Revise the relevance of the current EPR systems in relation to future needs and business automation Enhance access control for all campuses Evaluate effectiveness of current IT systems

STRATEGY Align ICT policies with current industry trends and regulations Enhance the use LMS tools to facilitate learning Communicate the rollout of the ICT strategic plan 2009-2012 Finalize effectiveness of IT ERP system or implement a new one by 2012/3

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Develop strategic plan | Strategic plan drafted for 2010- 2012 | Informed stakeholders Plans on operational level aligned with strat plan | D Ramasodi | Annual budget | 2010 | Communicate to stakeholders |
| Facilitate the implementation process of the ICT strategic plan | IT Dept to start rollout of ICT strategic plan | Systematic approach to implement ICT strat plan Implementation monitored and regular feedback inform re-planning/ adjustments | D Ramasodi | Annual budget | 2010 | Finalize and roll out of plan Communicate to stakeholders |
|  |  | Information gathered feeds into remedial action processes Satisfactory internal auditors reports Satisfactory external auditors reports | D Ramasodi | Annual budget | 2010 | Audit outcome should inform remedial actions on operational level |
| Develop mechanisms to ensure customer satisfaction and the enhancement of processes | IT Audit completed Recovery Plan in place | Satisfied customers Acceptable user satisfaction reports | D Ramasodi | Annual budget | 2010 | Communicate to stakeholders |

# RECOMMENDATION 14

The VUT recommends that as matter of urgency VUT reviews its certification process and puts in place necessary procedures and mechanisms to ensure integrity in the certification of its qualifications.

KEY PRIORITIES

Improve certification procedures and mechanism Ensure integrity in the certification of qualification

OBJECTIVES To ensure security of certificates issues by VUT To protect the integrity of the VUT certificates To put quality checks in place regarding the certification process

STRATEGY To select reputable suppliers for printing quality certificates To improve the process of certification To improve identification of students eligible for graduation for each session To conduct quality checks on certification for example through the 2% test

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Revision of process | Quality checks done by running default programme on ITS programme | Satisfactory external audit report Graduates should all be eligible for graduation | Snr Ass Regstr Exams | Approved budget | 2010 Ongoing Investigate – need to have identification of graduates by means of ITS | Completed |
|  | Planning benchmarking process Evaluate, redesign and redevelop the existing process and procedure Align process | Timely and accurate access to information Process aligned to national good practice | Snr Ass Regstr Exams | Dedicated funding | Ongoing | Completed Implement change process |
|  | Self-evaluation planned and conducted | Report to QPU/HEQC On par with HEQC standards for Deligated Functions External peer review report positive | Snr Ass Regstrr Exams Director QPU Snr Ass Regstrr Exams | QPU budget | 1999 Cyclical Reviews of QPU | Ongoing External peer review to be conducted |
| Mechanisms in place to ensure integrity of certificates | Technical preparation of certificates on par with best practice | VC and Registrar signatures with serial numbers on certificates | Snr Ass Registrar Exams | Dedicated allocation of funds | Ongoing | Completed |
|  | Up to date data base | Numbers appear on IT system | Snr Ass Registrar Exams | Dedicated allocation of funds | End of 2010 | Changes of the capturing of data to allow for automatic identification of graduates in process |
|  | Consistent administrative process | Each certificate signed by Exec Deans (Third signature) | Exec Deans Snr Ass Registrar Exams | Dedicated funds | Ongoing | Completed |
|  | Security of certificates on par with best practice | Printing by Shesha Printing | Snr Ass Regstrr Exams | Dedicated allocation of funds | March 2010 Ongoing | Completed |

# RECOMMENDATION 15

The HEQC recommends that VUT develops a database and a central process for approving and keeping records of institutional agreements with other entities.

KEY PRIORITIES

To establish a decision register and monitoring process of all external agreements with collaboration partners in order to facilitate effective implementation and monitoring of progress

OBJECTIVES Effective record keeping of all institutional agreements with collaboration partners

STRATEGY To develop an inclusive database to record all agreements with collaboration partners including appropriate detail to manage relationships and monitor of progress

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Development of a database | Establishment and development of an electronic database | Data base up to date | ED Research | Electronic database | 2010 | Database to be developed |
|  | Develop profile of collaboration partners and commitments | Detailed profile of partners | ED Research | Access to information on collaboration | Ongoing | Profile to be developed |
| Develop a central process for approving of agreements and keeping of records | Develop performance indicators to monitor the viability of relationships | Performance indicators on par with best practice | ED Research | Annual budget | 2010 | Revisit current processes and procedure |
|  | Introduce a monitoring cycle for all relationships | Regular monitoring and feedback | ED Research | Annual budget | Ongoing | Monitoring to be conducted on continuous basis after implementation |

# RECOMMENDATION 16

The HEQC recommends that VUT takes such steps as are necessary to ensure that appropriate academic staff acquire knowledge and skills in designing and developing pedagogically sound academic programmes which are both embedded in the institution’s strategic direction and responsive to the needs of relevant industries.

KEY PRIORITIES

Engagement with HEQF to effect the requirements (facilitated by Curriculum Development) Align industrial skills needs with exist level outcomes and level descriptors

OBJECTIVES Create opportunities for intellectual transfer and pursuit of knowledge. Create a student-centred environment accessible to individuals of diverse ages, cultures and socio-economic backgrounds. A commitment to engage in relevant research projects concerning academic staff development. Personal commitment to the development of staff members through staff development programmes and the recognition of performance.

STRATEGY Engagement commitment (based on real needs, curriculum development commitment, research collaboration, good neighbourliness). Encourage creativity, scholarship and entrepreneurial thought in its staff members and students. Promote local and international perspectives in the curriculum and among staff members and students. Compulsory staff development participation for all academic staff

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Develop initiatives for academic staff development | Teams to be established in accordance with the guidelines approved by senate Academic staff to be trained in programme development and appropriate teaching and teaching (e.g. ADHE module), first group of staff trained, second group 2010. Senate approval of training initiatives – assessor training of all academic staff (approved 2009) Academic Staff Development Programmes leased on new national imperatives in higher education | Programmes aligned with HEQF prescriptions and Communique 3 of the HEQC Guideline for Programme Developers available for implementation Number of trained staff Programme designing Curriculum, of Teaching Development processes developed Number of staff trained on online accreditation/ as assessors | Dir Cur Dev HoD’s | Academic Staff Development Officer Dedicated funding | 2009 Ongoing | Appointment of Academic Staff Development Officer |
| Designing of a new PQM | PQM designed for the VUT (new), approved by senate and DoHET | Approved PQM | Dir Cur Dev | Cur Dev Reps Dedicated funding | 2010 | PQM developed and approved Appointment of Cur Dev Reps |

# RECOMMENDATION 17

The HEQC recommends that the VUT institutes a comprehensive and systematic approach to monitoring the performance of subjects, including gathering data on grade distributions, progression, attrition and student evaluation of the subject – as a way of improving the quality of teaching and learning at the institution.

KEY PRIORITIES

Monitoring of data for decision making on continuous basis Improve MIS system Establish link between performance monitoring and plans for performance improvement

OBJECTIVES Develop processes that monitor academic performance Develop mechanisms that integrate MI with planning and remedial action initiatives

STRATEGY Develop a system that is effective to ensure continuous monitoring of progress and the improvement of intervention and processes to enhance the delivery of programmes

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPONSIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Identification of subjects/ programmes at risk | Monitoring of formative and summative results to determine poorly performing areas | High risk identification every semester Proof of ad-hoc interventions | HoD’s | Normal budget | Ongoing | Process ongoing to identify high risk per exam cycle |
| To develop appropriate instruments to facilitate the continuous monitoring of learning progress | Establish an IT instrument to flag all weak areas continuously Develop immediate intervention programmes as part of a pro-active learning facilitation process | Effective mechanisms are in place to monitor progress | HoD’s | Normal budget | Ongoing Busy finalizing an early warning system to be completed in 2010 | Continuous process to establish interventions to support such subject areas e.g. tutorials and peer programmes |

# RECOMMENDATION 18

The HEQC recommends that VUT takes steps to evaluate and monitor the application of the new assessment policy, particularly with regard to continuous assessment, the moderation system, and the integrity and security of records.

KEY PRIORITIES

Appropriate Assessment Policy Continuous assessment Moderation Security of records

OBJECTIVES Revise Assessment Regulation Policy Revise continuous assessment, moderation system and integrity of records

STRATEGY Revisit the assessment policy within the contects of the assessment method and approach. Aligns related policies and procedures with Assessment Regulation Policy Implement mechanisms that ensures the monitoring and integrity of records

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPONSIBILITY | RESOURCES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Revision of Assessment Policy and Procedures | Workshops with key role players Revision of policy and alignment with other related documents/ policies Alignment with approved Policy Guideline Document Approval of document and implementation Monitor the impact and quality of continuous assessment of learning | Policy revised and approved | Registrar: Academic Dir QPU | QPU Budget | 2009-2010 | Revision in process |

# RECOMMENDATION 19

The HEQC recommends that VUT considers reviewing the assigned roles, status and resourcing of the Research Committee to include responsibility for the development, implementation and monitoring of the research strategy of VUT.

KEY PRIORITIES

Revisit the mandate of the Research Committee Revisit the delegations of the Research Committee Identify PI’s for the Research Committee

OBJECTIVES To revisit the mandate of the Research Committee To develop PI’s To develop continuous monitoring of effectiveness of the CRC Reposition the CRC

STRATEGY To develop the CRC function i.t.o. clear PI’s to optimize its contribution to research development

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Redevelop the mandate and business model of the CRC | Revisit the mandate of the Research Committee Develop PI’s in relation to Research Strategy Evaluation by utilising PI’s | PI driven committee Annual quality reports reflecting on output and impact. | Dir Research | Available New Research Committee to be established in 2010 | 2009 Ongoing | Alignment Research Directorate, Senate and Faculty Strategic Plans and Activities |

# RECOMMENDATION 20

The HEQC recommends that VUT develops a more explicit and comprehensive policy on ethical clearance in order to protect the institution, the researcher and the external partners and communities involved in research projects.

KEY PRIORITIES

Effective implementation and utilisation of an ethics policy and process Ethics committee – sanctioning M and D dissertations Declaration of “own work” by students Guidelines to be established

OBJECTIVES Develop a benchmark of the Ethical Committee function in higher education Develop a policy i.t.o. ethical considerations in research Develop a structure to facilitate the implementation of continuous ethical research and research practices

STRATEGY Establish a multi-disciplinary ethics committee to assess research proposals towards ensuring appropriate ethical standards

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Develop processes for ethical clearance of projects and partnerships | Establish an Ethics Committee Develop processes for ethical clearance Develop policy and facilitate | Ethics Policy – approved Established committee | Dir Research | Research budget | 2009 ongoing | Completed Induction workshop for Committee members to be conducted |
|  | The implementation of policy | Processes developed and implemented |  | Research budget | Ongoing | Continuous monitoring of effectiveness and functional of the committee |

# RECOMMENDATION 21

The HEQC recommends that VUT considers the development of a strategy to encourage the development of research outputs, including publications, in the SET disciplines, in order to support the institution’s objective of becoming a UoT.

KEY PRIORITIES

Capacity building Enhanced Research outputs Growing Applied Contract Research Clear Research Focus Areas More staff involvement in Research Effective reporting criteria structures and for Research Institutes

OBJECTIVES Develop a supportive institutional culture and structure to enhance research at the VUT Establish effective research development programmes and related incentives to stimulate research development Develop research capacity to effectively follow multi-, inter- and trans- disciplinary options required to address the complex challenges of the knowledge environment Focus on establishing a research agenda which is responsive to specific needs in society/industry Introduce effective research capacity development into all programmes to develop knowledge creators and innovators rather than only users of knowledge Establish research networks to optimize capacity through exchange initiatives Achieve at least 0.5% research outputs per staff member by 2012

STRATEGY Establish a research culture based on appropriate capacity to facilitate relevant and quality research output

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESLPONSIBIITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Establish institutional capacity to facilitate focus areas institutes and centres of excellence | Develop criteria for the establishment of focus areas, institutes and centres of excellence Develop evaluation criteria to monitor effectiveness and efficiency of institutes and centres of excellence Develop clear mobility creteria and processes | Viable and sustainable focus areas, institutes and centres of excellence | Dir Research | Dedicated allocation of funds | 2007- Ongoing | Completed First Centre of Excellence established |
| Regular monitoring of the viability of research related entities (focus areas, institutes, etc) | Develop an audit and evaluation process to be implemented on annual basis | Annual audit report of all entities | Dir Research | Annual budget | 2007- Ongoing Feb 2010 | Completed Annual reports Developed Business Plans |
| Integrate time for research in the work load formula | Individual contracting to facilitate research output | Mentorships and programmes support research initiatives Staff contracts to facilitate research involvement | Dir Research | Dedicated allocation of funds | 2007- Ongoing | Completed Further implementation – next senate meeting Research and Faculty Plans |
| Regular focused training programmes | Annual schedule to develop research capacity of staff Annual report on programme development and its impact | Participants in training programmes | Dir Research | Research budget | 2007- Ongoing | Completed Programme for 2010 drafted and implemented |
| Establish support arrangements for researchers | Revisit the capacity of research office – to effectively guide and support researchers | Mentorships and programmes to support research initiatives | Dir Research | Research Development Officer to be appointed Administrative and professional support – need with regard to training programmes and fucntions | 2007- Ongoing | Completed – Research Development Officer appointed Additional administrative support appointed |
| Establish and promote funding and support and recognition processes | Define funding networks and opportunities Develop an information brochure on research funding opportunities Develop the capacity to support staff access to the opportunities | Policy and financial support | Dir Research | Research budget | 2007- Ongoing | Information brochure developed Ongoing Research Development Programmes, Grant and proposal writing sessions |
| Train staff i.t.o. MIT methodology | Develop focused programmes to build staff capacity i.t.o MIT research | Participants in training programme | Dir Research | Annual budgets | 2007- Ongoing | Integrated through Centre of Excellence |
| Introduce focused programmes to grow own timber | Identification of potential researchers Focus on development support programme to develop capacity Monitor progress of young/ developing researchers | Existing knowledge and methodology courses in all programmes | Dir Research | Hub and Spokes Model – R 2 million for 16 Scholarships | 2007- Ongoing | Annually R 2 million to be allocated |
| Introduce the hub and spokes model to support postgraduate work and introduce students into academic environment | Develop a business model to establish integrated training and research development opportunities for post graduate students Identify priority focus areas based on the research focus areas of the VUT | Operational hub and spokes model | Dir Research | Research budget | 2007- Ongoing | Completed – Postgraduate Induction Programme implemented rolled out across the institution based on current strengths |
| Establish industry-, community- and academic networks to inform the research agenda of the university | Develop an evaluation grid of potential contributors and stakeholders to research at the VUT Establish a differentiated framework of potential contributors and participants Establish interaction networks to facilitate regular interaction around specific initiatives | Research profile of new academic appointments | Dir Research |  | 2007- Ongoing | Differentiated framework of potential contributors and participants needs to be done |

# RECOMMENDATION 22

The HEQC recommends that VUT considers the most effective manner of formalizing and more fully developing organization-wide planning, monitoring, review and improvement systems in the area of research. Such systems need to be supported by an integrated information system and clearly defined roles of the various sources of support services for research, together with appropriate communication of their respective roles and activities.

KEY PRIORITIES Planning, monitoring and review system for research Information system to support management of research Defined roles of support services for research

OBJECTIVES Develop a system that ensures for continuous planning, review and enhancement of research Refine research support system

STRATEGY Focus on effective mechanisms for the generation of research management information

| INITIATIVES ON TACTICAL LEVEL | PLANS AND ACTIONS TAKEN | PERFOMANCE INDICATORS | RESPON- SIBILITY | RESOUR- CES | TIME | ALIGNMENT REQUIRED |
| --- | --- | --- | --- | --- | --- | --- |
| Develop a strategy | Establish a research monitoring and evaluation programme Introduce a continuous monitoring process of research related activities | PI for Research is developed | Director Research | Research budget | 2010 - Ongoing | Strategy developed |
| Introduce continuous planning and review system | Utilise minimum standards and performance indicators Introduce institutional system for ongoing improvement Integrate management information with planning and resource allocation Remedial action planning | Continuous processes of self-evaluation and peer reviews Annual evaluation profile of research development and future growth opportunities Outcomes feed into planning and re-planning Data and information are available for effective management of research | Research Director Dir Quality | QPU budget QPU staff | 2010 | Develop criteria Conduct pilot review Refine process/ evaluation instruments |